## Sheet1
Project: TimeTrackerApp
ID | Work Items | Hours | Hours Spend | Hours Remaining
1 | Provision Environment | 6 | 2 | 4
2 | Capture project names, set if project is billable or non billable and set the assign rate to the project. | 8 | 0.25 | 7.75
3 | Provide the ability to manually enter the amount of time they spend on a project for any day of a week. | 8 | 0 | 8
4 | Provide a timer allowing the user to capture the time they start and end a project that they work during the day. | 8 | 0 | 8
5 | Provide a weekly summary report | 16 | 0 | 16
| Total Hours | 46 | 2.25 | 43.75
Total Hours
| 2015-11-23 | 2015-11-24 | 2015-11-25 | 2015-11-26 | 2015-11-27
1 | 0.5 | 0.5 | 1 | 0 | 0 | 2
2 | 0 | 0.25 | 0 | 0 | 0 | 0.25
3 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0
| 2015-11-28 | 2015-11-29 | 2015-11-30 | 2015-12-01 | 2015-12-02
1 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0 | 0 | 0
3 | 0 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 0 | 0 | 0 | 0
5 | 0 | 0 | 0 | 0 | 0 | 0
| 2015-12-03 | 2015-12-04 | 2015-12-05 | 2015-12-06
1 | 0 | 0 | 0 | 0 |  | 0
2 | 0 | 0 | 0 | 0 |  | 0
3 | 0 | 0 | 0 | 0 |  | 0
4 | 0 | 0 | 0 | 0 |  | 0
5 | 0 | 0 | 0 | 0 |  | 0